# ACI Design Discussion - Detailed Technical Document

Meeting Date: August 26, 2025
Duration: 44 minutes
Document Version: 1.0
Classification: Technical Implementation Guide

## Table of Contents

- Meeting Context and Participants

- Current Infrastructure Analysis

- Technical Requirements and Constraints

- Proposed Architecture Design

- Implementation Strategy

- IPv6 Migration Planning

- Security Architecture

- Technical Challenges and Solutions

- Industry Best Practices

- Action Items and Timeline

## 1. Meeting Context and Participants

### Participant Profiles

#### John Barber - Network Compute Engineer (NCE)

- Role: On-site lead engineer at Clay Concern

- Tenure: 2.5 years at current position

- Background: Former Army, stationed in Germany

- Responsibilities: Primary ACI and data center networking

- Current Focus: Legacy equipment migration and ACI redesign

#### Eric Helgeson - WWT Engineer

- Coverage: European theater support

- Experience: 10 years supporting European customers, 20 years in Germany

- Collaboration: Working with Rita Younger and Mike Woody on ACI solutions

- Historical Context: Familiar with customer's fragmented procurement history

#### Rita Younger - WWT Practice Lead

- Expertise: 30+ years Cisco networking experience

- Position: Data Center Networking Practice Lead at WWT

- Background: Former Cisco Advanced Services instructor and CSAT program participant

- Location: St. Louis, Missouri

- Notable: Daughter works as Fed SEM at Cisco

#### Belete Ageze - Cisco Architect

- Role: Customer Delivery Architect

- Sector: US Public Sector

- Relationship: Long-standing relationship with John Barber

- Focus: ACI design and implementation guidance

### Meeting Objectives

- Establish consensus on ACI redesign approach

- Address IPv6 requirements and limitations

- Determine firewall integration strategy

- Define migration phases and priorities

- Align on technical implementation details

## 2. Current Infrastructure Analysis

### Network Architecture Overview

#### Physical Infrastructure

- Current Legacy Equipment:

  - Nexus 5K switches (acting as Layer 2 access switches)

  - Multiple FEX units for port expansion

  - VPC connections from 5Ks to ACI fabric

  - All VLANs trunked through 5K switches

- ACI Deployment:

  - Version: ACI 6.0.7

  - NDO Version: 4.1.x (requiring upgrade for ESG support)

  - Controllers: 3 per site configuration

  - Multi-site: 2 primary sites + 1 remote leaf location

#### Logical Configuration

- Tenant Structure: Multiple tenants (considering single tenant migration)

- VRFs: 8-9 Virtual Routing and Forwarding instances

- Bridge Domains: 192 configured

- EPGs: 192 End Point Groups (1:1 with Bridge Domains)

- Current Mode: Network-centric (VLAN-based segmentation)

- Inter-VRF Communication: VZANY per VRF

- External Routing: L3Outs to firewalls at each site

### Infrastructure Dependencies

#### Compute Infrastructure

- VMware Environment: Currently connected via legacy 5K switches

- UCS Platform: Hanging off 5K infrastructure

- Storage: Connected through legacy switching

- VMM Integration: Not currently implemented

#### Network Services

- Firewalls: Upgrading to new FirePower appliances

- Load Balancers: F5 devices (routing strategy TBD)

- Inter-Site Connectivity: ISN (Inter-Site Network) established

- Remote Sites: Connected via remote leaf architecture

### Historical Context

The ACI implementation was originally deployed 4-5 years ago as an emergency replacement for failing Nexus 7K switches. The deployment was:

- Rushed due to network outages

- Implemented without proper planning

- Procured in fragments over time

- Met with internal resistance ("fought" by staff)

- Never fully utilized for intended capabilities

## 3. Technical Requirements and Constraints

### Organizational Mandates

#### IPv6 Requirements (High Priority)

- Mandate: Full IPv6 implementation across infrastructure

- Approach: Dual-stack configuration (IPv4 + IPv6)

- Timeline: Elevated to top priority, possibly superseding redesign

- Scope: All L3Outs, bridge domains, and external routing

#### Modernization Goals

- Replace all legacy 5K/FEX infrastructure

- Implement true application-centric networking

- Improve security through micro-segmentation

- Reduce operational complexity

- Enable automation capabilities

### Technical Constraints

#### Version Dependencies

- ESG Multi-site Support: Requires latest versions

  - ACI: 6.2+ recommended

  - NDO: 4.2+ required

- IPv6 Limitations:

  - Underlay: IPv4 only (IPv6 planned for 6.2.1)

  - Overlay: Full IPv6 support available

  - VXLAN tunnels over ISN: Not supported for IPv6

#### Resource Limitations

- Tools:

  - No Tetration or similar application dependency mapping

  - Limited to NDI for visibility

  - ServiceNow potentially available

- Budget:

  - No funding for advanced analytics tools

  - Professional services limited

- Staffing:

  - Single on-site engineer (John)

  - Remote support from WWT and Cisco

### Compliance Requirements

- DoD Standards: Must maintain security compliance

- Change Management: Extensive "rock drill" exercises required

- Documentation: Comprehensive design documentation needed

- Testing: Thorough validation before production changes

## 4. Proposed Architecture Design

### Target State Architecture

#### Tenant Design

- Structure: Single tenant model

- Rationale:

  - Simplified management

  - Easier troubleshooting

  - Reduced complexity for small team

  - Sufficient for current requirements

#### VRF Strategy

- Approach: Maintain existing VRF structure initially

- Mapping: Align new Bridge Domains and EPGs with current VRFs

- Evolution: Gradual consolidation based on application requirements

#### Endpoint Group Strategy

##### Phase 1: Foundation

Current State (192 EPGs) → Single ESG Migration

- Create one ESG per VRF initially

- Maintain VZANY for universal communication

- Map existing EPGs to single ESG

##### Phase 2: Selective Segmentation

Single ESG → Application-Based ESGs

- Identify critical applications

- Create dedicated ESGs per application

- Implement contracts between ESGs

- Maintain backward compatibility

##### Phase 3: Full Segmentation

Application ESGs → Micro-segmentation

- Complete application dependency mapping

- Granular security policies

- Full contract implementation

- Remove VZANY dependencies

### VMM Integration Architecture

#### VMware Integration Design

- Domain Type: VMM Domain for vCenter

- Scope: All VMware clusters

- Benefits:

  - Dynamic EPG assignment

  - Automated VLAN provisioning

  - Improved visibility

  - Simplified operations

#### Implementation Approach

- Create VMM domain in ACI

- Establish vCenter connectivity

- Associate with physical infrastructure

- Migrate VMs gradually

- Validate and optimize

### Bridge Domain Design

#### Consolidation Strategy

- Current: 192 Bridge Domains (1:1 with VLANs)

- Target: Consolidated based on routing requirements

- Approach:

- Per VRF: Create logical Bridge Domains- Production_Web_BD- Production_App_BD- Production_DB_BD- DMZ_Services_BD- Management_BD

#### Subnet Management

- Maintain existing IP schemes initially

- Plan for IPv6 dual-stack per BD

- Optimize subnet sizes based on actual usage

- Document all changes thoroughly

## 5. Implementation Strategy

### Phase 1: Infrastructure Modernization (0-3 months)

#### Week 1-2: Preparation

- [ ] Complete network documentation

- [ ] Inventory all connections on 5K/FEX

- [ ] Develop migration runbooks

- [ ] Create rollback procedures

#### Week 3-4: VMM Integration

- [ ] Configure VMM domain

- [ ] Test with non-production cluster

- [ ] Document procedures

- [ ] Train operations team

#### Week 5-12: Legacy Migration

- [ ] Install new leaf switches

- [ ] Migrate connections from 5K/FEX

- [ ] Validate connectivity

- [ ] Decommission legacy equipment

### Phase 2: ACI Optimization (3-6 months)

#### Platform Upgrades

Current State:

- ACI: 6.0.7

- NDO: 4.1.x

Target State:

- ACI: 6.2.x (recommended release)

- NDO: 4.2.x (ESG multi-site support)

#### ESG Implementation

- Single ESG Creation

  - One ESG per VRF

  - Include all EPGs

  - Maintain VZANY

- Testing and Validation

  - Verify all communication paths

  - Document any issues

  - Performance benchmarking

- Gradual Migration

  - Start with test/dev environments

  - Move to production systematically

  - Maintain rollback capability

### Phase 3: Application-Centric Transformation (6-12 months)

#### Application Discovery Process

##### Automated Discovery

Tools and Methods:

1. NDI Analytics

- Flow analysis

- Endpoint tracking

- Protocol identification

2. ServiceNow Integration

- CMDB correlation

- Application mapping

- Dependency tracking

3. Python Scripts

- Parse existing configs

- Generate topology maps

- Identify communication patterns

##### Manual Discovery

- Interview application owners

- Review documentation

- Analyze firewall rules

- Examine load balancer configs

#### ESG Segmentation Strategy

##### Critical Applications First

- Identify top 5 critical applications

- Map all dependencies

- Create dedicated ESGs

- Implement specific contracts

- Test thoroughly

- Monitor and optimize

##### Iterative Refinement

- Weekly review cycles

- Continuous optimization

- Performance monitoring

- Security validation

## 6. IPv6 Migration Planning

### Current IPv6 Support Matrix

| Component | IPv4 Support | IPv6 Support | Notes |
| --- | --- | --- | --- |
| Underlay | ✅ Full | ❌ Not Available | Planned for 6.2.1 |
| Overlay | ✅ Full | ✅ Full | Available now |
| Bridge Domains | ✅ Full | ✅ Dual-stack | Supported |
| L3Outs | ✅ Full | ✅ Dual-stack | Supported |
| EPGs | ✅ Full | ✅ Full | Supported |
| Contracts | ✅ Full | ✅ Full | Supported |
| Multi-site ISN | ✅ Full | ⚠️ Limited | No VXLAN over IPv6 |

### Implementation Approach

#### Dual-Stack Configuration

##### Bridge Domain Level

Configuration Steps:

1. Enable IPv6 on Bridge Domain

2. Configure IPv6 gateway

3. Set IPv6 specific parameters:

- ND Policy

- RA Policy

- DAD (Duplicate Address Detection)

##### L3Out Configuration

External Routing:

1. Configure IPv6 on L3Out interfaces

2. Establish BGP IPv6 address family

3. Configure route maps for IPv6

4. Implement prefix lists

#### Multi-Site Considerations

##### Current Limitations

- VXLAN tunnels require IPv4 underlay

- ISN connectivity IPv4-based

- BGP EVPN uses IPv4 transport

##### Workaround Strategy

- Maintain IPv4 for infrastructure

- Implement IPv6 for user traffic

- Use dual-stack at all layers

- Plan for future full IPv6

### Testing and Validation

#### Test Plan Components

- Connectivity Testing

  - Intra-subnet IPv6

  - Inter-subnet routing

  - External connectivity

  - Multi-site communication

- Application Testing

  - IPv6-only applications

  - Dual-stack applications

  - Legacy IPv4 compatibility

  - Performance comparison

- Security Validation

  - Contract enforcement

  - Firewall policies

  - ACL implementation

  - Traffic inspection

## 7. Security Architecture

### Firewall Integration Strategy

#### Current State

- Traffic Flow: Hair-pinning through firewalls for inter-VRF

- Placement: External to ACI fabric

- Management: Separate from ACI policy

#### Recommended Approach

##### North-South Security (Maintain)

Internet → Firewall → ACI Border Leaf → Internal Resources

- Traditional perimeter security

- Centralized threat management

- Simplified troubleshooting

##### East-West Security (ESG-Based)

ESG1 ← Contract → ESG2

- Micro-segmentation via ESGs

- Distributed security policy

- No firewall hair-pinning

- Better performance

#### Decision Rationale

Against Service Graph/PBR:

- Adds complexity in multi-site

- Difficult troubleshooting

- Performance implications

- Limited value with ESGs

For ESG-Based Security:

- Native ACI capability

- Simplified operations

- Better performance

- Sufficient security

### Contract Design Strategy

#### Hierarchical Contract Model

##### Tier 1: Infrastructure Contracts

Common Services:

- DNS_Contract

- NTP_Contract

- AD_Contract

- Management_Contract

##### Tier 2: Application Contracts

Application-Specific:

- Web_to_App_Contract

- App_to_DB_Contract

- External_Access_Contract

##### Tier 3: Security Zones

Zone-Based:

- DMZ_to_Internal_Contract

- Production_to_Development_Contract

- User_to_Services_Contract

### Compliance Considerations

#### DoD Security Requirements

- Mandatory access controls

- Audit logging

- Encryption requirements

- Separation of duties

#### Implementation Approach

- Map requirements to ACI capabilities

- Implement RBAC in ACI

- Enable comprehensive logging

- Regular security audits

## 8. Technical Challenges and Solutions

### Challenge 1: Application Dependency Mapping

#### Problem

- No automated discovery tools

- Complex application interactions

- Undocumented dependencies

- Risk of breaking communications

#### Solution Approach

# Phased Discovery Process

Phase 1: Baseline Current Flows

- Use NDI for flow analysis

- Capture during peak periods

- Document all communications

Phase 2: Categorize Traffic

- Sort by application

- Identify critical paths

- Map dependencies

Phase 3: Incremental Testing

- Start with non-critical apps

- Test in maintenance windows

- Build confidence gradually

### Challenge 2: Limited Resources

#### Problem

- Single engineer on-site

- No dedicated application team

- Limited budget for tools

- Time constraints

#### Solution Approach

- Leverage automation (Python/Ansible)

- Utilize WWT/Cisco support

- Implement in phases

- Focus on high-impact changes

### Challenge 3: Organizational Resistance

#### Problem

- Historical negative experience with ACI

- Preference for traditional networking

- Fear of complexity

- Change resistance

#### Solution Approach

- Education and Training

  - On-site workshops

  - Hands-on demonstrations

  - Success story sharing

  - Gradual adoption

- Quick Wins

  - VMM integration benefits

  - Simplified operations

  - Improved visibility

  - Automation examples

- Stakeholder Engagement

  - Regular updates

  - Clear communication

  - Demonstrated value

  - Risk mitigation

### Challenge 4: Multi-Site Complexity

#### Problem

- ISN configuration

- Site synchronization

- Stretched VLANs

- Disaster recovery

#### Solution Approach

- Keep design simple initially

- Avoid complex service graphs

- Maintain site autonomy

- Plan for site isolation

## 9. Industry Best Practices

### Comparison with Other Deployments

#### EUCOM and AFRICOM Approach

- Strategy: Network-centric, one-for-one migration

- Rationale: Simplicity and speed

- Results: Successful migration with minimal disruption

- Lesson: Don't overcomplicate initial migration

#### Enterprise Trends

##### Movement to NDFC

- Drivers:

  - Reduced complexity

  - Familiar CLI

  - Easier operations

  - Group Policy Objects for segmentation

- Considerations:

  - Still provides segmentation

  - Simpler than ACI

  - Better for network-centric teams

##### Arista Competition

- Warning: Cloud Vision more complex than ACI

- Recommendation: Stay with Cisco ecosystem

- Alternative: Consider NDFC if ACI too complex

### WWT Recommendations

Based on extensive customer experience:

- Start Simple

  - Network-centric initially

  - Single tenant design

  - Minimal contracts

  - Focus on stability

- VMM Integration Priority

  - Immediate operational benefits

  - Simplified provisioning

  - Better visibility

  - Foundation for automation

- Incremental Migration

  - Avoid "big bang" approaches

  - Test thoroughly

  - Maintain rollback options

  - Document everything

- Application-Centric Evolution

  - Only for critical applications

  - Requires dependency mapping

  - Start with low-risk apps

  - Build expertise gradually

## 10. Action Items and Timeline

### Immediate Actions (Week 1-2)

| Action Item | Owner | Due Date | Status |
| --- | --- | --- | --- |
| Send network diagrams to WWT | John Barber | Week 1 | Pending |
| Review current documentation | Rita Younger | Week 1 | Pending |
| Schedule on-site workshop | Eric Helgeson | Week 2 | Pending |
| Brief Conrad on approach | John Barber | Upon return | Pending |

### Short-term Actions (Month 1-2)

| Action Item | Owner | Target | Priority |
| --- | --- | --- | --- |
| Complete 5K migration planning | John | Month 1 | High |
| Deploy VMM integration | John | Month 1 | High |
| Test IPv6 in lab | John/Belete | Month 2 | Medium |
| Create automation scripts | John | Month 2 | Medium |

### Medium-term Actions (Month 3-6)

| Action Item | Owner | Target | Priority |
| --- | --- | --- | --- |
| Upgrade ACI/NDO versions | John | Month 3 | High |
| Implement single ESG | John | Month 4 | High |
| Begin application mapping | Team | Month 5 | Medium |
| Deploy IPv6 dual-stack | John | Month 6 | High |

### Long-term Actions (Month 6-12)

| Action Item | Owner | Target | Priority |
| --- | --- | --- | --- |
| Create application ESGs | John | Month 8 | Medium |
| Implement contracts | John | Month 10 | Medium |
| Complete documentation | Team | Month 12 | High |
| Conduct security audit | Team | Month 12 | High |

### Success Criteria

#### Phase 1 Success Metrics

- ✅ All 5K/FEX equipment replaced

- ✅ VMM integration operational

- ✅ No service disruptions

- ✅ Team trained on new processes

#### Phase 2 Success Metrics

- ✅ IPv6 dual-stack deployed

- ✅ Single ESG implemented

- ✅ Platform versions current

- ✅ Automation tools deployed

#### Phase 3 Success Metrics

- ✅ 25% applications in dedicated ESGs

- ✅ Contract policies implemented

- ✅ Full documentation complete

- ✅ Operational efficiency improved

## Appendices

### A. Technical Resources

#### Cisco Documentation

- ACI Configuration Guide

- ESG Implementation Guide

- IPv6 Deployment Guide

- Multi-Site Configuration

#### WWT Resources

- Mike Woody's Lab Environments

- Learning Paths

- Best Practice Guides

- Customer Case Studies

### B. Contact Information

| Name | Role | Email | Availability |
| --- | --- | --- | --- |
| John Barber | NCE Lead | [TBD] | On-site |
| Eric Helgeson | WWT Engineer | [TBD] | Europe TZ |
| Rita Younger | WWT Practice Lead | [TBD] | US Central |
| Belete Ageze | Cisco CDA | [TBD] | US Eastern |
| Mike Woody | WWT SME | [TBD] | US Central |

### C. Glossary of Terms

| Term | Definition |
| --- | --- |
| ACI | Application Centric Infrastructure |
| ESG | Endpoint Security Group |
| EPG | Endpoint Group |
| NDO | Nexus Dashboard Orchestrator |
| NDI | Nexus Dashboard Insights |
| NDFC | Nexus Dashboard Fabric Controller |
| VMM | Virtual Machine Manager |
| VRF | Virtual Routing and Forwarding |
| ISN | Inter-Site Network |
| VZANY | Contract permitting any-to-any communication within VRF |
| PBR | Policy-Based Redirect |

### D. Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Application breakage during ESG migration | Medium | High | Thorough testing, gradual migration |
| IPv6 compatibility issues | Low | Medium | Dual-stack approach, extensive testing |
| Resource constraints delay project | High | Medium | Automation, external support |
| Organizational resistance | Medium | Medium | Education, quick wins, communication |

Document Version Control:

- Version 1.0 - Initial Release - September 2025

- Review Cycle: Monthly

- Next Review: October 2025

- Distribution: Internal Technical Team

Classification: Technical Implementation Document
Restrictions: Internal Use Only
Owner: Network Engineering Team