## Slide 1
ACI Redesign
Executive Summary
AEDCG + AEDCK · 2-VRF design · Design A (UCS-FI direct attach) · IaC end-to-end
39
EPGs (consolidated from 266)
2
VRFs (down from 11)
39
BDs (down from 215)
100%
Terraform-managed
Prepared April 2026 · Network Engineering · Confidential, internal use

## Slide 2
What this is
One-page view of why we are doing this and what changes
EXECUTIVE SUMMARY
Why
• Today's design is 11 VRFs, 215 bridge domains, 266 endpoint groups grown organically over years.
• Every change requires a long maintenance window because blast radius is unclear.
• Front-end Nexus 5K switches add a hop, a failure domain, and a license/support cost we can retire.
• There is no single source of truth — drift between APIC and Excel/runbooks is constant.
What
• Collapse to 2 VRFs (internal + DMZ) with vzAny permit-all baseline; tighten with ESGs over time.
• Consolidate to 39 BDs / 39 EPGs grouped by function, not by VLAN number.
• Move ESXi traffic onto an APIC-managed VDS (per-fabric APCG-VDS1, APCK-VDS1).
• Connect UCS Fabric Interconnects directly to ACI leaves (Design A) — N5Ks decommissioned.
• All of it is described as YAML and applied via Terraform + GitLab CI.
Impact
• No IP renumbering. No VLAN renumbering for VM workloads. No application changes.
• Cutover is staged: policy push first (zero traffic impact), then physical re-cable in a maintenance window.
• Lab is already cut over and validated. Production is ready pending a change window and a few decisions.
• After cutover: faster, safer changes; smaller blast radius; automated drift detection.
Same applications. Same IPs. Cleaner network. Safer change path.
ACI Redesign — Executive Summary
2 / 13

## Slide 3
Today vs. After
The numeric and operational delta in one view
EXECUTIVE SUMMARY
Dimension | Today | After redesign | Why it matters
VRFs | 11 | 2 (VRF-EUR + VRF-DMZ) | Easier to reason about traffic flow
Bridge Domains | 215 | 39 | Functional grouping replaces ad-hoc per-VLAN BDs
Endpoint Groups | 266 | 39 | Consolidated by workload type
Endpoint Security Groups | 0 | Future (vzAny first) | Phased tightening of policy without re-cabling
L3Outs | 13 | Unchanged (legacy) | Out of scope for this cutover; managed by the existing ndo-terraform repo
VMware integration | VMM1 (single, manual VLAN tagging) | Per-fabric APCG-VDS1 / APCK-VDS1 (dynamic) | ACI manages VLANs, port-groups, host uplinks
Front-end switching | Nexus 5K vPC fronting UCS | UCS FIs directly attached to ACI (Design A) | One fewer device per path; N5Ks decommissioned
Configuration source of truth | GUI + spreadsheets | YAML + Terraform + Git | Reviewable, auditable, reproducible
Change pipeline | Manual, ticket-driven | GitLab CI: validate → plan → manual deploy | Plan reviewed before any APIC/NDO write
Counts sourced from production NDO schema AEDCE / AppProf-NetCentric and docs/reports/bd_mapping_analysis.txt.
ACI Redesign — Executive Summary
3 / 13

## Slide 4
Target Architecture (Design A)
UCS Fabric Interconnects directly attached to ACI leaves
EXECUTIVE SUMMARY
Site AEDCG
Leaves 152 + 153 · APCG-VDS1 · PC_FI_A → eth1/6 · PC_FI_B → eth1/7
ACI leaves (spine-attached, ESG/EPG enforcement)
Port-channels PC_FI_A · PC_FI_B (mac-pin)
UCS Fabric Interconnects FI-A · FI-B
UCS B-series blade chassis
ESXi hosts (VTEP, vmkernel mgmt on EPG-VHOST-MGMT)
APIC-managed VDS (port-groups = redesign EPGs)
Site AEDCK
Leaves 119 + 191 · APCK-VDS1 · PC_FI_A → eth1/6 · PC_FI_B → eth1/7
ACI leaves (spine-attached, ESG/EPG enforcement)
Port-channels PC_FI_A · PC_FI_B (mac-pin)
UCS Fabric Interconnects FI-A · FI-B
UCS B-series blade chassis
ESXi hosts (VTEP, vmkernel mgmt on EPG-VHOST-MGMT)
APIC-managed VDS (port-groups = redesign EPGs)
Tenant tree (2 VRFs, 39 BDs, 39 EPGs, contracts) is pushed once from NDO to BOTH sites simultaneously.
Each APIC owns its own per-fabric access policies and adopts its own pre-existing per-fabric VDS.
ACI Redesign — Executive Summary
4 / 13

## Slide 5
What does NOT change
The redesign is non-disruptive on these dimensions
EXECUTIVE SUMMARY
User-visible state is preserved
• IP addressing
  ◦ Every existing subnet keeps its IP. Bridge-domain consolidation absorbs subnets, never re-numbers them.
• Application traffic
  ◦ vzAny permit-all in each VRF preserves all current intra-VRF flows. No application owner has to do anything.
• VM workloads
  ◦ VMs land on the new APIC-managed VDS via a vMotion-equivalent port-group migration. No guest reconfiguration.
• Tenant boundaries
  ◦ Tenant EUR is unchanged. The redesign sits inside it.
Adjacent systems are untouched
• North-south routing (L3Outs)
  ◦ The 13 existing L3Outs stay where they are, managed by the legacy ndo-terraform repo. Same external peers, same routes.
• vCenter
  ◦ Same vCenter instance, same datacenter, same hosts. ACI adopts the existing per-fabric VDS rather than creating a new one.
• Hostnames, DNS, AD
  ◦ All identity-side dependencies are untouched.
• Operational ownership
  ◦ Same network, virtualisation, and UCS teams. Tooling changes internally; the operating model stays the same.
ACI Redesign — Executive Summary
5 / 13

## Slide 6
Cutover Plan
Five gated stages — first three are reversible without traffic impact
EXECUTIVE SUMMARY
Stage | Action | Detail | Traffic impact | 
1 | APIC access / fabric policies | Push new VLAN pools, AAEPs, port-channels, leaf profiles, per-fabric VMM domains. | None — additive only | 
2 | Tenant tree via NDO | Push 2 VRFs, 39 BDs, 39 EPGs, vzAny contracts. Bind EPGs to per-fabric VDSes. | None — VMs stay on legacy port-groups until Stage 4 | 
3 | Static port bindings | PATCH non-VM EPGs (load balancer, radio gateways, ESXi vmkernel) into NDO via curated JSON. | None — bindings activate on the existing physical paths | 
4 | UCS / vCenter physical move | Re-cable FI uplinks from N5K to ACI leaves. Migrate VM port-groups to the new VDS. | Brief blip per host pair as VDS uplinks move | 
5 | Decommission | After 24-hour soak: retire legacy VMM bindings and N5K front-end. | None | 
GREEN
GREEN
GREEN
AMBER
GREEN
Pre-flight (T-7 days) and rollback are codified in the Production cutover runbook (aci-redesign/README.md)
APIC + NDO + vCenter snapshots before Stage 1 · deploy jobs gated when:manual on main · every stage has an explicit verify and rollback step
ACI Redesign — Executive Summary
6 / 13

## Slide 7
Risks & Rollback
Top three risks with named mitigation and rollback target
EXECUTIVE SUMMARY
Risk | Why it can happen | Mitigation | Rollback
VLAN-collision on static bindings | Multiple legacy EPGs consolidating into one redesign EPG can produce two VLANs on the same path/EPG, which APIC rejects. | Pick a VLAN winner per (path, EPG) pair before the cutover. Run the bindings dump tool, review, edit, re-run. | Stage 3 NDO undeploy + remove bindings — non-VMM EPGs revert to no-binding.
UCS / FI cabling mismatch | Production FI uplinks are assumed on eth1/6 and eth1/7. If actual cabling differs, APIC won't program the bundle until YAML is corrected. | Walk the cabling worksheet with UCS team in pre-flight. Per-leaf interface profiles are easy to amend in YAML. | Stage 1 destroy / partial-fabric apply — additive only, rolls back in <60s.
NDO push collides with same-named APIC-local objects | The first NDO deploy can detect existing tenant objects with matching names and need to absorb them. | Plan reviewed before deploy. Deploy is manual (when:manual). Lab cutover already validated this path. | Stage 2 NDO undeploy + terraform destroy on ndo/ root. Legacy IPv6 schema is in a separate state, untouched.
Stages 1-3 are reversible with no traffic impact
Only Stage 4 (physical re-cable + VDS uplink move) carries any traffic risk, and that risk is per-host blips, not site-wide outage. Worst case is restoring from APIC + NDO snapshots taken in pre-flight.
ACI Redesign — Executive Summary
7 / 13

## Slide 8
Status
Where we are right now
EXECUTIVE SUMMARY
LAB
DONE
• Per-fabric VMM domains (APCG-VDS1, APCK-VDS1) deployed and adopted from existing VDSes in shared vCenter.
• Tenant tree pushed via NDO: 2 VRFs, 39 BDs, 39 EPGs, vzAny contracts; deploy validated.
• 39 port-groups visible in vCenter on each VDS, across 3 ESXi hosts per site.
• All access/fabric policies match the netascode/nac-aci module's expected schema; no plan diffs.
PRODUCTION
STAGED
• Production Terraform root (apic-vmware-prod/) created and lints clean; mirrors lab structure.
• Production access policies committed for both fabrics: PC_FI_A/B, fi-static-vlan-pool (213 VLANs), leaf 152/153 + 119/191 split.
• GitLab CI jobs added: validate-aci-prod, plan-aci-prod, deploy-aci-prod (manual gate). Same for ndo-redesign root.
• Cutover runbook documented in aci-redesign/README.md.
OUTSTANDING
DECISIONS NEEDED
• Generate the production static-bindings JSON (read-only dump from prod NDO).
• Choose a VLAN-winner policy where multiple legacy EPGs consolidate onto one redesign EPG.
• Confirm UCS FI uplink ports (assumed eth1/6, eth1/7).
• Schedule the maintenance window for Stage 4 (physical FI re-cable + VDS uplink migration).
ACI Redesign — Executive Summary
8 / 13

## Slide 9
Operational Benefits After Cutover
What changes about how we run the network day-to-day
EXECUTIVE SUMMARY
Activity | How it works after cutover | Why it matters
Add a new EPG / workload | Edit YAML → MR → CI plan → manual deploy | Days → minutes; reviewable plan; no GUI clicks
Onboard a new VM | Land VM on the right port-group on the VDS | Zero APIC change; ACI tracks endpoints automatically
Tighten security | Add ESGs and contracts incrementally; vzAny serves as the safety net | Phased path; no flag-day
Detect drift | GitLab CI plan job runs on every change | Discrepancies surface in MR review, not in production
Recover from misconfig | Revert MR → CI re-plans → manual deploy | Rollback is a Git operation
Disaster recovery | Snapshots + Terraform state + Git history | Same fabric configuration can be re-pushed to a rebuilt APIC in hours, not days
Audit / compliance | Every change is a Git commit + GitLab pipeline + Terraform state row | Single chain of evidence per change
Front-end switching cost | N5Ks decommissioned at end of cutover | License / support / power savings; one less failure domain in the data path
ACI Redesign — Executive Summary
9 / 13

## Slide 10
Decisions Needed
Inputs the cutover plan is waiting on
EXECUTIVE SUMMARY
Decision | Why it's needed | Owner | Recommendation
VLAN-winner policy | Some redesign EPGs consolidate multiple legacy EPGs that were on different VLANs. APIC accepts only one VLAN per (path, EPG) pair. | Network Engineering | Three reasonable defaults: lowest VLAN wins, highest endpoint-count wins, or hand-curated. Recommend endpoint-count for least disruption.
Production maintenance window | Stage 4 (physical FI re-cable, VDS uplink migration) needs a coordinated window across Network, UCS, and Virtualisation. | Change Advisory Board | Recommended: a single 4-hour window per site, two weeks apart so rollback signal is clear before site B.
UCS FI port mapping confirmation | Production data files assume FI-A → eth1/6 and FI-B → eth1/7. UCS team to confirm or correct. | UCS Engineering | Quick check; YAML edit if different. No code change required.
L3Out scope | Decision already made: L3Outs stay in the legacy ndo-terraform schema for this cutover. Revisit after stabilisation. | Network Architecture | Confirmed; documented in schema header and runbook.
ESG / micro-segmentation roadmap | Initial design uses vzAny permit-all. ESG-based tightening is deferred until the Terraform module supports them. | Security + Network | Tracked as a follow-up; lab runs vzAny today without issue.
ACI Redesign — Executive Summary
10 / 13

## Slide 11
Indicative Timeline
Right-to-left: each box is days, not weeks
EXECUTIVE SUMMARY
DONE
Lab cutover
T-7 days
Bindings JSON + collision review
T-3 days
Pre-flight snapshots + plans
T-0 morning
Stage 1-3 policy + tenant + bindings
T-0 window
Stage 4 FI re-cable + VDS uplinks
T+1 to T+7
Stage 5 decommission
Total active engineering effort during the change window: ~4-6 hours per site.
Timeline assumes a single change-window per site, with AEDCG and AEDCK cut over two weeks apart so issues at site A surface before site B is touched.
Concrete dates set once VLAN-winner policy + UCS port confirmation are in.
ACI Redesign — Executive Summary
11 / 13

## Slide 12
Ask
What we need from this audience
EXECUTIVE SUMMARY
Decisions / approvals
• Approve the cutover approach
  ◦ Single-window-per-site, Design A (UCS-FI direct attach), deploy gated when:manual.
• Sponsor the maintenance window
  ◦ Two 4-hour windows, two weeks apart (AEDCG then AEDCK). Network, UCS, and Virtualisation owners on the bridge.
• Sign off on VLAN-winner policy
  ◦ Recommend: highest endpoint-count wins for each consolidated EPG.
• Confirm UCS FI port assumption
  ◦ FI-A → eth1/6, FI-B → eth1/7 on each leaf pair. UCS team to validate or adjust.
• Acknowledge deferred items
  ◦ L3Out reorganisation and ESG-based micro-segmentation are follow-ups, not part of this cutover.
Everything else is built, lab-validated, in source control, and CI-gated.
ACI Redesign — Executive Summary
12 / 13

## Slide 13
Where to dig deeper
Pointers for engineers and reviewers
EXECUTIVE SUMMARY
Topic | Path | What you'll find
Strategy deck (technical) | aci-redesign/ACI_Redesign_Strategy.pptx | 27 slides covering the full design, BD mapping, phased security, deployment design decisions.
Production cutover runbook | aci-redesign/README.md → 'Production cutover runbook' section | Pre-flight, 5-stage sequence with verify steps, per-stage rollback table.
NDO schema (single source of truth) | aci-redesign/data/nac-ndo/schema-aedce-ipv4.nac.yaml | 2 VRFs, 39 BDs, 39 EPGs, vzAny + 2 contracts. Header documents all in-scope and out-of-scope items.
Production access policies | aci-redesign/data/nac-aci-{aedcg,aedck}-prod/access-policies.nac.yaml | Design A: PC_FI_A/B, fi-static-vlan-pool, leaf splits.
Terraform roots | aci-redesign/{apic-vmware,ndo,apic-vmware-prod}/ | Lab APIC root, NDO redesign root, production APIC root. Each has its own Makefile, scripts, and CI jobs.
Bindings tooling | aci-redesign/scripts/{dump_bindings.py,deploy_bindings.py} | Read-only dump from prod NDO; PATCH static bindings into the redesign schema.
GitLab CI | .gitlab-ci.yml | validate-aci, plan-aci, deploy-aci (lab) + validate-aci-prod, plan-aci-prod, deploy-aci-prod (prod, manual gate) + validate/plan/deploy-ndo-redesign.
Repository: terraform_redesign_esg (GitLab: root/terraform_redesign_esg)
ACI Redesign — Executive Summary
13 / 13